Things to do.

1. Isolate DNA for sequencing (3 Months March-July 2015).
	1. Determine how best to get HQ DNA
	2. Scale to 96 well plate
	3. Isolate Enough for Sequencing
	4. Sequence
2. Spawning Season Year 2 (3 Months May-August 2015)
	1. Visit sites when temps appropriate
	2. Collect larvae
	3. Every Two weeks?
	4. Undergrads/Assistants?
3. Bioinformatics Analysis (7 Months April-October 2015)
	1. ASTER model?
	2. STACKS pipeline
	3. STRUCTURE?
	4. GenePop?
4. Write Genomics Manuscript/Thesis (7 Months August 2015 - February 2016)
	1. Methods (August)
	2. Introduction (September)
	3. Results (October)
	4. Discussion (November)
	5. Revision (December-January)
	6. Submission (February)
5. Fish 310 (April-June 2015)
	1. Teaching
	2. Grading
	3. Preparing
	4. Field Trip
	5. Drinking