## Sheet1
Supply/Material | Quantity | Need to purchase? | Cost
6 levels pCO2 | 6
TA samples | 153
spec pH samples | 153
water bath | 1
large beakers for bath | 3
DI water | na
second water bath | 1
thermometers (3) | 3
lab tape | 2
mesh bags (18) | 18
labels for bags | 18
liquid N2 | ? | yes | 87
RNAlater | 2
screw cap tubes | 1200 | yes | 189
sample boxes | 12.5
VWR pens | 2
forceps | 2
bleach | na
95% EtOH | FHL
sterile sand | bottle
small beakers/bottles for washing | 2
histology casettes (240) | 240 | yes | 100
Invertebrate Davidson's
Jars for fixation | FHL
70% EtOH | FHL
Jars for EtOH | FHL
pen for labeling casettes | 1 | yes | 56.54
Shellfish Diet | 1 | yes | 44
Concentrated HCl |  | yes | 32.55
P1000 pipette tips | 2
Waste for Davidson's
Kim wipes | 2
cooler for oysters | 2
scissors | 2
scalpel | 1
scalpel blades | 10 | yes | 12
m-cresol purple | 1
p200 tips | 5
sample bottles | 20
CRMs | 15
HgCl2 | 1
50 mL serologicals | 10
calipers | 1
shuckers | 2
CO2 | 2 | yes | 60
TOTAL |  |  | 581.09

## Sheet2
Week | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 7
Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43
Date | time axis 2011-12-30 to 2012-02-10
pH | bar: 2011-12-30; 2012-01-01 to 2012-01-06; 2012-01-08; 2012-01-10; 2012-01-12; 2012-01-14; 2012-01-16; 2012-01-18; 2012-01-20; 2012-01-22; 2012-01-24; 2012-01-26; 2012-01-28; 2012-01-30; 2012-02-01; 2012-02-03; 2012-02-05; 2012-02-07; 2012-02-09
Alkalinity | [43 empty] | TOTAL TA AND PH SAMPLES | bar: 2012-01-01 to 2012-01-04; 2012-01-06; 2012-01-08; 2012-01-10; 2012-01-12; 2012-01-14; 2012-01-16; 2012-01-18; 2012-01-20; 2012-01-22; 2012-01-24; 2012-01-26; 2012-01-28; 2012-01-30; 2012-02-01; 2012-02-03; 2012-02-05; 2012-02-07; 2012-02-09
Total daily samples | 2011-12-30: 3; 2012-01-01: 3; 2012-01-02: 3; 2012-01-03: 3; 2012-01-04: 3; 2012-01-05: 3; 2012-01-06: 18; 2012-01-08: 18; 2012-01-10: 6; 2012-01-12: 6; 2012-01-14: 7; 2012-01-16: 7; 2012-01-18: 7; 2012-01-20: 6; 2012-01-22: 6; 2012-01-24: 6; 2012-01-26: 6; 2012-01-28: 6; 2012-01-30: 6; 2012-02-01: 6; 2012-02-03: 6; 2012-02-05: 6; 2012-02-07: 6; 2012-02-09: 6 | 153
OA | 2011-12-30: Acclimation; 2011-12-31: Acclimation; 2012-01-01: Acclimation; 2012-01-02: Acclimation; 2012-01-03: Acclimation; 2012-01-04: Acclimation; 2012-01-05: Acclimation; 2012-01-06: Exposure begins; 2012-01-13: 1 wk exposure ends; 2012-02-03: 1 month exposure ends
Temperature | 2012-01-02: Find LHT; 2012-01-03: Find LHT; 2012-01-04: Find LHT; 2012-01-05: Find LHT; 2012-01-06: Find LHT; 2012-01-07: Find LHT; 2012-01-08: Find LHT; 2012-01-13: SLT and LHT; 2012-01-15: LHT; 2012-01-20: LHT; 2012-02-03: LHT and SLT; 2012-02-05: SLT; 2012-02-10: SLT
samples taken from treatment water and from 2 vessels
acclimation will occur in 3 tanks
for week 2, 6 tanks with reps of 8 will be in use
after week 2, 6 tanks with reps of 4
also during week 1, need to test which dripper to use
maybe need 7th tank for weeks 2 and 3 for LHT